## Slide 1: Planning and Managing the Project: Effort Estimation

## Slide 2: Effort Estimation
Estimating project costs is one of the crucial aspects of project planning and management
Estimating cost has to be done as early as possible during the project life cycle

## Slide 3: Types of Costs
Facilities: hardware, space, furniture, telephone, etc.
Software tools for designing software
Staff (effort): the biggest component of cost

## Slide 4: Software Project Estimation
S/W cost and effort estimation will never be an exact science
  Too many variables
    Human
    Technical
    Environmental
    Political

## Slide 5: Effort Estimation Estimation Should be Done Repeatedly
Uncertainty early in the project can affect the accuracy of cost and size estimations

## Slide 6: Pre-requisite to Estimating Effort
Understand the scope of the project to be built
Generate an estimate of size

## Slide 7: Estimating Size
The accuracy of a s/w project estimate is predicated on a number of things:
  The degree to which the planner has properly estimated the size of the product to be built
  The ability to translate the size estimate into human effort, calendar time, and dollars (required availability of past records)
  The degree to which the project plan reflects the abilities of the s/w team
  The stability of product requirements and the environment that supports the s/w engineering effort

## Slide 8: Estimating Size
Sizing represents the project planner’s first major challenge
Size refers to a quantifiable outcome of the s/w project (e.g. LOC and/or FP)

## Slide 9: Estimating Size and Effort
Example of baseline productivity metrics are LOC/pm or FP/pm

## Slide 10: An Example
Software Module | Estimated LOC
User interface and control facilities (UICF) Two-dimensional geometric analysis (2DGA) Three-dimensional geometric analysis (3DGA) Database management (DBM) Computer graphics display facilities (CGDF) Peripheral control function (PCF) Design analysis modules (DAM) | 2,300 5,300 6,800 3,350 4,950 2,100 8,400
Estimated lines of code | 33,200
Effort?
Productivity?

## Slide 11: An Example of LOC-Based Estimation
Estimated lines of code = W = 33,200
Let,
  Average productivity = X = 50 LOC/pd
  Labor rate = Y = $100 per day
So,
  Cost per line of code = Z = Y/X = $2
  Total estimated project cost = W*Z = $66,400
  Estimated effort = W/X = 664 person-days

## Slide 12: An Example of LOC-Based Estimation
Estimated lines of code = W = 33,200
Let,
  Average productivity = X = 600 LOC/pm
  Labor rate = Y = $5000 per month
So,
  Cost per line of code = Z = Y/X = ?
  Total estimated project cost = W*Z = ?
  Estimated effort = W/X = ?

## Slide 13: 3.3 Effort Estimation Sidebar 3.3 Causes of Inaccurate Estimates
Key causes
  Frequent request for change by users
  Overlooked tasks
  User's lack of understanding of the requirements
  Insufficient analysis when developing estimates
  Lack of coordination of system development, technical services, operations, data administration, and other functions during development
  Lack of an adequate method or guidelines for estimating

## Slide 14: 3.3 Effort Estimation Sidebar 3.3 Causes of Inaccurate Estimates (continued)
Key influences
  Complexity of the proposed application system
  Required integration with existing system
  Complexity of the program in the system
  Size of the system expressed as number of functions or programs
  Capabilities of the project team members
  Project team's experience with the application, the programming language, and hardware
  Capabilities of the project team members
  Database management system
  Number of project team member
  Extent of programming and documentation standards

## Slide 15: Software Project Estimation
  Base estimates on similar projects that have already been completed
    Unfortunately, past experience has not always been a good indicator of future results but it helps
  Use relatively simple decomposition techniques to generate project cost and effort estimates
    “Divide and conquer” approach
  Use one or more empirical models for software cost and effort estimation
    Can be used as a cross-check for the previous option and vice versa

## Slide 16: Decomposition Techniques
  Decompose the problem into sub-problems
  Understand the scope of the s/w to be built
  Generate an estimate of its “size”

## Slide 17: Estimating Size
A hierarchy of estimation models
Address the following areas
  Application composition model
  Early design stage model
  Post-architecture stage model
Three different sizing options are available
  Application points
  Function points
  Lines of source code

## Slide 18: Effort Estimation COCOMO
Introduced by Boehm
COCOMO I
  effort as a function of size
COCOMO II
  updated version
  effort as a function of size
  Includes cost factors as a multiplier
  include models of reuse
  requires sizing information like all other models
COnstructive COst MOdel (COCOMO)

## Slide 19: Effort Estimation COCOMO I
Effort (E) = a (KLOC)b person_months
Development Time (D) = c x E d months
Organic: small teams, rigid requirements
Semi detached: medium teams, less rigid requirements
Embedded: combination of O and S (h/w, s/w,…)
S/W Type | a | b | c | d
Org | 2.4 | 1.05 | 2.5 | 0.38
Sdet | 3 | 1.12 | 2.5 | 0.35
Emb | 3.6 | 1.20 | 2.5 | 0.32

## Slide 20: An Example
Software Module | Estimated LOC
User interface and control facilities (UICF) Two-dimensional geometric analysis (2DGA) Three-dimensional geometric analysis (3DGA) Database management (DBM) Computer graphics display facilities (CGDF) Peripheral control function (PCF) Design analysis modules (DAM) | 2,300 5,300 6,800 3,350 4,950 2,100 8,400
Estimated lines of code | 33,200
E?
D?
Productivity?

## Slide 21: Effort Estimation COCOMO II: Stages of Development
Effort = b (S)c m(x) person_months
Application composition
  prototyping to resolve high-risk user interface issues
  size estimates in application points
Early design
  to explore alternative architectures and concepts
  size estimates in function points
Postarchitecture
  development has begun
  size estimates in lines of code

## Slide 22: Three Stages of COCOMO II

## Slide 23: Estimating Size: Stage 1
Application points are computed using counts of the number of
  Screens (at the user interface)
  Reports
  Components likely to be required to build the application

## Slide 24
Estimating Size: Stage 1

## Slide 25: Estimating Size: Stage 1
Object type | Complexity weight |  | 
 | Simple | Medium | Difficult
Screen | 1 | 2 | 3
Report | 2 | 5 | 8
Components |  |  | 10
Complexity weights for object types

## Slide 26: Estimating Size: Stage 1
Developer’s experience/capability | Very low | Low | Nominal | High | Very High
Environment maturity/capability | Very low | Low | Nominal | High | Very High
PROD | 4 | 7 | 13 | 25 | 50
Productivity rate for object points

## Slide 27: Estimation of Size
Example of baseline productivity metrics are LOC/pm or FP/pm
Making the use of single baseline productivity metric is discouraged
In general, LOC/pm or FP/pm averages should be computed by project domain
Local domain averages should be used

## Slide 28
Function Points (FP) Can be used effectively as a means for measuring the functionality delivered by a system
Using historical data, function points can be used to
  Estimate the cost or effort required to design, code, and test the software
  Predict the number of errors that will be encountered during testing
  Forecast the number of components and/or the number of projected source code lines in the implemented system
Derived using an empirical relationship based on
  Countable (direct) measures of the software’s information domain
  Assessments of the software’s complexity
FP = count total * [0.65 + 0.01 * sum(Fi)]
Estimating Size: Stage 2

## Slide 29: Introduction to Function Points
Information Domain Values
  Number of external inputs
  Number of external outputs
  Number of external inquiries
  Number of internal logical files
  Number of external interface files
Value Adjustment Factors (VAF)
  14 Factors

## Slide 30: Information Domain Values
Number of external inputs
  Each external input originates from a user or is transmitted from another application
  They provide distinct application-oriented data or control information
  They are often used to update internal logical files
  They are not inquiries (those are counted under another category)
Number of external outputs
  Each external output is derived within the application and provides information to the user
  This refers to reports, screens, error messages, etc.
  Individual data items within a report or screen are not counted separately

## Slide 31: Information Domain Values (continued)
Number of external inquiries
  An external inquiry is defined as an online input that results in the generation of some immediate software response
  The response is in the form of an on-line output
Number of internal logical files
  Each internal logical file is a logical grouping of data that resides within the application’s boundary and is maintained via external inputs
Number of external interface files
  Each external interface file is a logical grouping of data that resides external to the application but provides data that may be of use to the application

## Slide 32: Value Adjustment Factors
Does the system require reliable backup and recovery?
Are specialized data communications required to transfer information to or from the application?
Are there distributed processing functions?
Is performance critical?
Will the system run in an existing, heavily utilized operational environment?
Does the system require on-line data entry?
Does the on-line data entry require the input transaction to be built over multiple screens or operations?

## Slide 33: Value Adjustment Factors (continued)
Are the internal logical files updated on-line?
Are the inputs, outputs, files, or inquiries complex?
Is the internal processing complex?
Is the code designed to be reusable?
Are conversion and installation included in the design?
Is the system designed for multiple installations in different organizations?
Is the application designed to facilitate change and for ease of use by the user?

## Slide 34: Function Point Computation
Identify/collect the information domain values
Complete the table shown below to get the count total (aka unadjusted function points)
  Associate a weighting factor (i.e., complexity value) with each count based on criteria established by the software development organization
Evaluate and sum up the adjustment factors (see example in the next few slides)
  “Fi” refers to 14 value adjustment factors, with each ranging in value from 0 (not important) to 5 (absolutely essential)
Compute the number of function points (FP) aka Adjusted FP FP = count total * [0.65 + 0.01 * sum(Fi)]
Information Weighting Factor
Domain Value Count Simple Average Complex
External Inputs _____ x 3 4 6 = _____
External Outputs _____ x 4 5 7 = _____
External Inquiries _____ x 3 4 6 = _____
Internal Logical Files _____ x 7 10 15 = _____
External Interface Files _____ x 5 7 10 = _____ Count total ________

## Slide 35: Function Point Example
FP = count total * [0.65 + 0.01 * sum(Fi)]
FP = 50 * [0.65 + 0.01 * 46]
FP = 55.5 (rounded up to 56)
Information Weighting Factor
Domain Value Count Simple Average Complex
External Inputs 3 x 3 4 6 = 9
External Outputs 2 x 4 5 7 = 8
External Inquiries 2 x 3 4 6 = 6
Internal Logical Files 1 x 7 10 15 = 7
External Interface Files 4 x 5 7 10 = 20 Count total 50

## Slide 36: An Example of FP-Based Estimation
Information Domain Value | Count |  | Weighting factor |  |  |  | 
 |  |  | Simple | Average | Complex |  | 
External Inputs (EIS) | 6 | X | 3 | 4 | 6 | = | 
External Outputs (EOs) | 3 | X | 4 | 5 | 7 | = | 
External Inquiries (EQs) | 5 | X | 3 | 4 | 6 | = | 
Internal Logical Files (ILFs) | 2 | X | 7 | 10 | 15 | = | 
External Interface Files (EIFs) | 4 | X | 5 | 7 | 10 | = | 
Count Total |  |  |  |  |  |  | 
Computing function points

## Slide 37: An Example of FP-Based Estimation
Value Adjustment Factors

## Slide 38: An Example of FP-Based Estimation
Now,
  FPestimated = count_total  [0.65 + 0.01   (Fi)]
    Fi (i = 1 to 14 are value adjustment factors)
So,
  FPestimated = W = 320  [0.65 + 0.01  52] = 375 (approx.)
Let,
  Average Productivity = X = 6.5 FP/pm
  Labor rate = Y = $8,000 per month
So,
  Cost per FP = Z = Y/X = $1,230 (approx.)
  Total estimated project cost = W*Z = $461,000 (approx.)
  Estimated effort = W/X = 58 person months (approx)

## Slide 39: An Example
password, panic button, activate/deactivate
zone inquiry, sensor inquiry
system configuration file
messages, sensor status
test sensor, zone setting, alarm alert, a/d
Let ΣFi = 46
Size in FP?
Effort?
Cost?

## Slide 40: Estimating Size: Stage 3
See slides 9 to 12

## Slide 41: Information System Example Piccadilly System estimate at stage 1 (Application Composition Time)
Using COCOMO II
Three screens and one report
  Booking screen: complexity simple, weight 1
  Ratecard screen: complexity simple, weight 1
  Availability screen: complexity medium, weight 2
  Sales report: complexity medium, weight 5
Low experience and low CASE maturity
Estimated effort = 1.29 person months

## Slide 42: Management Activities in SE
Estimation in Agile Development (Recap)
Discussed before Mid 1

## Slide 43: Estimation in Agile
Project Velocity
  The amount of work an agile team can complete in a sprint
Story Points
  The amount of effort required to implement a user story
User Story
  A requirement or general explanation of software feature

## Slide 44: Examples of User Stories
As a [customer], I want [shopping cart feature] so that [I can easily purchase items online].
As an [manager], I want to [generate a report] so that [I can understand which departments need more resources].
As a [customer], I want to [receive an SMS when the item is arrived] so that [I can go pick it up right away]

## Slide 45: Example

## Slide 46: Estimation in Agile
Project Velocity
  Story points completed ÷ Number of sprints

## Slide 47: References
SE by Pfleeger
SE by Pressman
UCF slides for SE course